## Cost Analysis
Employee Type | Median Annual Salary | Weeks of Work | Total Cost
Software Engineer for Database | 69131 | 9 | 11964.9808
Software Engineer for Android | 69131 | 7 | 9306.0962
Software Engineer for Web Application | 69131 | 10 | 13294.4231
UI Designer for Android | 62137 | 3 | 3584.8269
Web Designer for Web Application | 44894 | 5 | 4316.7308
Database Administrator | 69263 | 5 | 6659.9038
Total Employee Cost |  |  | 49126.9615
Equipment | Unit Cost | Units Required | Total Cost
Developer Machine | 750 | 6 | 4500
Android Phones for Development/Testing | 349 | 2 | 698
Server Computer | 1129 | 1 | 1129
Server Enterprise Class Hard Drive | 220 | 1 | 220
Oracle Database Software | 17500 | 1 | 17500
Total Equipment Cost |  |  | 24047
Projected Total Cost |  |  | 66626.9615

## Source Code Estimation
Database Application | Lines of Code in Prototype
Add Bag Servlet | 66
Create Collection Log Servlet | 98
Get Logs Servlet | 96
Verify User Servlet | 71
Total | 331
Android Application | Lines of Code In Prototype | Lines of XML for Layout
Add Bag Activity | 83 | 100
Login Activity | 171 | 57
Main Options Screen | 44 | 35
Record Collection Info Screen | 235 | 70
Total | 533 | 262
Web Application | Lines of Javascript | Lines of HTML
Login Page | 22 | 54
Main Menu Page | 0 | 228
Outstanding Logs Page | 41 | 110
Log Details | 61 | 105
Total | 124 | 497
Total Lines of Business Logic Code | 988
Total Lines of UI Code | 759